## ResBack Gantt
GANTT CHART FOR THE PROJECT
Project: | Development of a Web-Based Anonymous Feedback System for CCIS Students Using Sentiment Analysis and Algorithmic Concern Ranking
Project Team: | Team Mira
Methodology: | Agile Data Science 2.0
PHASES | TASKS (ACTIVITIES) | RESPONSIBLE | START DATE | END DATE | PROGRESS | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | DELIVERABLE
Preparation | Review literature on sentiment analysis and concern ranking | Team Lead (Viloria) | 2026-08-03 | 2026-08-05 | For confirmation | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Literature review
| Study existing anonymous feedback systems | All Members | 2026-08-06 | 2026-08-08 | For confirmation | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Comparative analysis
| Assess pretrained sentiment models and API options | Lead Dev (Queypo) | 2026-08-06 | 2026-08-09 | For confirmation | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Technology assessment
| Research concern-ranking methods | Lead Dev (Queypo) | 2026-08-09 | 2026-08-11 | For confirmation | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Ranking-method review
| Prepare data-gathering instruments | Doc Lead (Orenza) | 2026-08-08 | 2026-08-10 | For confirmation | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Survey and interview instruments
| Conduct interviews and surveys | Team Lead (Viloria) | 2026-08-11 | 2026-08-14 | For confirmation | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Survey and interview results
| Identify functional and non-functional requirements | Team Lead & Doc Lead | 2026-08-12 | 2026-08-16 | For confirmation | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Software requirements
| Analyze problems and stakeholder needs | All Members | 2026-08-15 | 2026-08-18 | For confirmation | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Problem statement
| Prioritize requirements and analytical deliverables | Team Lead & Developers | 2026-08-19 | 2026-08-21 | For confirmation | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Prioritized development tasks
| Define iteration goals and evaluation criteria | Team Lead & Developers | 2026-08-21 | 2026-08-22 | For confirmation | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Iteration goals and criteria
| Design system architecture | Lead Dev (Queypo) | 2026-08-20 | 2026-08-23 | For confirmation | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Architecture diagram
| Create interface wireframes | UI/UX Dev (Queypo) | 2026-08-21 | 2026-08-25 | For confirmation | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Interface wireframes
| Set up the development environment | Lead Dev (Queypo) | 2026-08-26 | 2026-08-28 | For confirmation | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Development environment
| Develop the interface prototype | UI/UX Dev (Queypo) | 2026-08-26 | 2026-09-04 | For confirmation | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Interface prototype
Records | Design the feedback and analysis database schema | Lead Dev (Queypo) | 2026-08-22 | 2026-08-24 | For confirmation | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Database schema
| Set up the database and backend | Lead Dev (Queypo) | 2026-08-28 | 2026-09-02 | For confirmation | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Database and backend
| Implement authentication and role permissions | Lead Dev (Queypo) | 2026-09-03 | 2026-09-08 | For confirmation | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Authentication and access rules
| Develop feedback submission and input screening | Lead Dev (Queypo) | 2026-09-09 | 2026-09-14 | For confirmation | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Validated feedback submission
| Implement anonymous feedback presentation | Lead Dev (Queypo) | 2026-09-12 | 2026-09-17 | For confirmation | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Submitter identity protection
| Store feedback and analysis status records | Lead Dev (Queypo) | 2026-09-15 | 2026-09-20 | For confirmation | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Feedback and analysis records
| Develop the feedback submission interface | UI/UX Dev (Queypo) | 2026-09-14 | 2026-09-20 | For confirmation | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Feedback interface
| Configure Gemma through the Gemini API | Lead Dev (Queypo) | 2026-09-19 | 2026-09-21 | For confirmation | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Model and API configuration
| Validate text and normalize duplicate checks | Lead Dev (Queypo) | 2026-09-22 | 2026-09-25 | For confirmation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Input and duplicate validation
| Integrate sentiment, topic and language analysis | Lead Dev (Queypo) | 2026-09-24 | 2026-09-30 | For confirmation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | Validated analysis outputs
Charts | Display sentiment and analysis results | UI/UX Dev (Queypo) | 2026-09-30 | 2026-10-02 | For confirmation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Sentiment result views
| Build dashboard charts and verify filtered totals | UI/UX Dev (Queypo) | 2026-10-11 | 2026-10-18 | For confirmation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | Sentiment, language and trend charts
Reports | Develop feedback reports and shared filters | Lead Dev (Queypo) | 2026-10-14 | 2026-10-20 | For confirmation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | Filtered feedback reports
| Export reports to PDF and Excel | Lead Dev (Queypo) | 2026-10-21 | 2026-10-24 | For confirmation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | PDF and XLSX exports
Recommendations | Design weighted concern-ranking rules | Lead Dev (Queypo) | 2026-10-01 | 2026-10-05 | For confirmation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | Volume, sentiment, confidence and recency rules
| Implement topic grouping and weighted ranking | Lead Dev (Queypo) | 2026-10-04 | 2026-10-10 | For confirmation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | Concern-ranking implementation
| Validate ranking weights and low-evidence indicators | Lead Dev (Queypo) | 2026-10-09 | 2026-10-14 | For confirmation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | Controlled ranking test results
| Display ranked concerns with supporting examples | UI/UX Dev (Queypo) | 2026-10-11 | 2026-10-14 | For confirmation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | Ranked concerns and evidence
Actions | Conduct user acceptance testing and stakeholder review | QA Tester (Viloria) | 2026-10-25 | 2026-10-28 | For confirmation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | UAT results and review findings
| Refine data, prompts and interfaces from review findings | Lead Dev (Queypo) | 2026-10-26 | 2026-10-30 | For confirmation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Refined system
Testing and iteration | Review results and iterate across the five data-value stages | All Members | 2026-08-26 | 2026-10-31 | For confirmation | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Iteration review log
| Evaluate initial sentiment outputs against human labels | QA Tester (Viloria) | 2026-09-28 | 2026-10-02 | For confirmation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Initial sentiment evaluation
| Run unit tests and fix defects | All Members | 2026-10-18 | 2026-10-24 | For confirmation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | Unit test results and fixes
| Test the integrated feedback-to-report workflow | QA Tester (Viloria) | 2026-10-22 | 2026-10-26 | For confirmation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Integration and system test report
| Evaluate sentiment performance against human labels | QA Tester (Viloria) | 2026-10-23 | 2026-10-26 | For confirmation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Accuracy, precision, recall and F1 results
Documentation and delivery | Configure and verify local and online deployment | Lead Dev (Queypo) | 2026-10-18 | 2026-10-22 | For confirmation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | Local and online deployment checks
| Prepare presentation materials | UI/UX Dev (Queypo) | 2026-10-25 | 2026-10-28 | For confirmation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Presentation deck
| Complete technical documentation and diagrams | Doc Lead (Orenza) | 2026-10-25 | 2026-10-30 | For confirmation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Technical documentation
| Conduct the internal presentation rehearsal | All Members | 2026-10-29 | 2026-10-31 | For confirmation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Presentation rehearsal